## Product-Backlog
PRODUCT BACKLOG IDINE MODULE
PRODUCT BACKLOG REPORT
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
101 | As an admin. | I want to create employee accounts | so that staff members can access the banking system. | High | 1 | In Progress | Not Started | High
102 | As an admin. | I want to assign roles (Admin, Manager, Teller). | so that access to features is controlled properly. | High | 1 | In Progress | In Progress | Medium
103 | As an admin | I want to activate or deactivate employee accounts. | so that only authorized staff can use the system | Medium | 3 | Not Started | Complete | Low
104 | As an admin | I want to view staff activity logs | so that I can monitor employee actions. | Medium | 4 | Not Started | Overdue
105 | As a system administrator | I want to deploy the application securely on Azure. | so that the system is accessible and scalable in the cloud. | Medium | 5 | Not Started | On Hold
106 | As a manager | I want to verify customer KYC status, | so that compliance requirements are met | High | 5 | Not Started
107 | As a manager | I want to close or freeze an account, | so that suspicious or inactive accounts are controlled. | Medium | 6 | Not Started
108 | As a manager | I want to approve or reject loan applications, | so that financial risk is managed.. | Medium | 7 | Not Started
109 | As a manager | I want to view dashboard statistics (total customers, deposits, loans), | so that I can monitor overall bank performance. | High | 4 | Not Started
110 | As an employee | I want to log in securely using my credentials, | so that I can access authorized banking operations. | High | 1 | Not Started
111 | As a bank teller | I want to register a new customer, | so that the customer can open bank accounts. | High | 1 | Not Started
112 | As a bank employee | I want to update customer details | so that customer information remains accurate. | Medium | 2 | Not Started
113 | As a bank employee | I want to search customers with pagination and filters. | so that customer information remains accurate. | Medium | 2 | Not Started
114 | As a bank teller | I want to open a savings or current account, | so that customers can perform transactions. | High | 3 | Not Started
115 | As a bank employee | I want to view account balance details, | so that I can provide accurate information. | High | 3 | Not Started
116 | As a bank employee | I want to deposit money into an account. | so that the customer’s balance increases. | High | 7 | Not Started
117 | As a bank teller | I want to withdraw money from an account. | so that customers can receive their funds. | High | 6 | Not Started
118 | As a bank employee | I want to transfer funds between accounts. | so that customers can move money securely. | High | 7 | Not Started
119 | As a bank employee | I want to view transaction history with date filters | so that transactions can be tracked and audited. | Medium | 7 | Not Started
120 | As a bank employee. | I want to generate account statements | so that customers can review their transaction history. | Medium | 7 | Not Started
121 | As a customer. | I want to apply for a loan, | so that I can borrow money from the bank. | Medium | 7 | Not Started
122 | As a customer, | I want to repay my loan installments, | so that I can clear my outstanding loan amount. | Medium | 7 | Not Started
123 | As a system, | I want to lock an account after multiple failed login attempts | so that unauthorized access is prevented. | High | 7 | Not Started
124 | As a system,. | I want to enforce minimum balance rules, | so that account policies are maintained. | High | 7 | Not Started
125 | As a system,. | I want fund transfers to be processed atomically, | so that debit and credit operations remain consistent. | High | 7 | Not Started
126 | As a system,. | I want to maintain double-entry ledger records | so that all financial transactions are accurately accounted for. | High | 7 | Not Started
127 | As a system,. | I want to log all user activities and transactions | so that audit and compliance requirements are fulfilled. | High | 7 | Not Started
128 | As a system, | I want to calculate EMI automatically, | so that loan repayment schedules are structured correctly. | Medium | 7 | Not Started
129 | As a system, | I want to monitor application logs and errors | so that issues can be detected and resolved quickly. | Low | 7 | Not Started

## Sprint-Backlog
AGILE SPRINT BACKLOG IDINE
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #101- User Authentication & Secure Access Setup
Design and implement secure login system with credential validation and JWT token management. |  | Saksham Boliya | In Progress
Develop forgot password and reset password functionality with secure token handling. |  | Saksham Boliya | In Progress
Implement role-based authorization for Admin, Manager, and Employee access control. |  | Saksham Boliya | In Progress
Apply password hashing (BCrypt), input validation, and authentication flow testing. |  | Saksham Boliya | In Progress
User Story #102 – Customer Registration & Management
Design customer entity and configure database relationships. |  | Saksham Boliya | In Progress
Develop API to register new customer with validation rules. |  | Saksham Boliya | In Progress
Implement update and soft delete functionality for customer records. |  | Saksham Boliya | In Progress
Implement search with pagination and filtering features. Perform integration testing with frontend forms. |  | Saksham Boliya | Not Started
User Story #103 – Account Creation & Lifecycle Management
Design account entity with Customer relationship mapping. Develop account opening functionality with unique account number generation |  | Saksham Boliya | Not Started
Implement account freeze and close functionality. |  | Saksham Boliya | Not Started
Implement minimum balance validation rules. |  | Saksham Boliya | Not Started
Perform account module testing and validation. |  | Saksham Boliya | Not Started
User Story #104 – Deposit & Withdrawal Operations
Develop deposit API with balance update logic. Develop withdrawal API with sufficient balance validation. |  | Saksham Boliya | Not Started
Ensure transaction records are stored in database. |  | Saksham Boliya | Not Started
Implement concurrency handling to prevent double withdrawals. |  | Saksham Boliya | Not Started
Perform integration testing of transaction flows. |  | Saksham Boliya | Not Started
User Story #105 – Fund Transfer & Atomic Transactions
Design fund transfer service with debit and credit logic. Implement database transaction handling using BeginTransaction(). |  | Saksham Boliya | Not Started
Implement rollback mechanism in case of failure. |  | Saksham Boliya | Not Started
Create double-entry ledger records for each transfer. |  | Saksham Boliya | Not Started
Perform end-to-end testing of transfer scenarios. |  | Saksham Boliya | Not Started
User Story #106 – Loan Management & EMI Processing
Design loan entity and repayment schedule structure. Develop loan application API with validation |  | Saksham Boliya | Not Started
Implement manager approval/rejection workflow. |  | Saksham Boliya | Not Started
Develop EMI calculation logic and schedule generation. |  | Saksham Boliya | Not Started
Implement loan repayment tracking and update loan status. |  | Saksham Boliya | Not Started
User Story #107 – Audit Logging, Reports & Dashboard
Design audit log entity to track system activities. Implement logging for login attempts and transactions. |  | Saksham Boliya | Not Started
Develop account statement generation with date filtering. |  | Saksham Boliya | Not Started
Create dashboard statistics for total customers, deposits, and loans. |  | Saksham Boliya | Not Started
Integrate Application Insights for monitoring and error tracking. |  | Saksham Boliya | Not Started
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## User story
S.NO | User Story | Acceptance Criteria
1 | As an employee, I want to log in securely so that I can access the banking system.
3 | As a bank employee, I want to open a savings or current account so that customers can perform transactions | Given a valid customer ID When the employee opens an account Then a unique account number is generated. Given an invalid customer ID When account creation is attempted Then an error message is displayed
4 | As a bank teller, I want to deposit money into an account so that the customer’s balance increases.
5
6 | As a bank employee, I want to transfer funds between accounts so that customers can move money securely. | Given valid source and destination accounts When the transfer is processed Then the amount is debited from source and credited to destination. Given insufficient balance When transfer is attempted Then the transaction is cancelled.
7 | As a bank employee, I want to view transaction history so that transactions can be tracked and audited..
8 | As a customer, I want to apply for a loan so that I can borrow money from the bank | Given valid loan details When the loan application is submitted Then the loan status is set to Pending. Given missing information When the form is submitted Then validation errors are displayed.
9 | As a manager, I want to approve or reject loan applications so that financial risk is managed. | Given a pending loan application When the manager approves it Then the loan status becomes Approved. Given a pending loan application When the manager rejects it Then the loan status becomes Rejected.
10 | As a system, I want to log all transactions and user activities so that audit and compliance requirements are fulfilled. | Given any transaction When it is completed Then a log entry is created. Given a failed login attempt When it occurs Then it is recorded in the audit log.
11 | As a manager, I want to verify customer KYC status so that compliance requirements are met. | Given a customer with pending KYC When the manager verifies the documents Then the KYC status is updated to Verified. Given invalid or incomplete documents When the manager reviews them Then the KYC status remains Pending and an error is shown.
`12 | As a system, I want fund transfers to be processed atomically so that debit and credit operations remain consistent. | Given valid source and destination accounts When a transfer is initiated Then both debit and credit operations are completed successfully. Given a failure during the transfer process When the system detects the error Then the entire transaction is rolled back and no balance is changed.
13 | As a system, I want to calculate EMI automatically so that loan repayment schedules are structured correctly. | Given valid loan amount, interest rate, and tenure When the loan is approved Then the EMI amount is calculated correctly. Given calculated EMI details When the schedule is generated Then repayment dates and installment amounts are stored in the system.
Given valid customer details When the employee submits the form Then a new customer record is created.
Given missing required fields When the form is submitted Then validation errors are displayed.
As a bank employee, I want to register a new customer so that they can open an account.
2
Given valid credentials When the user logs in Then access is granted.
Given invalid credentials When the user logs in Then an error message is shown.
Given multiple failed login attempts When the failed attempts exceed the limit Then the account is locked.
Given a valid account number When transaction history is requested Then all related transactions are displayed.
Given date filters When filters are applied Then only filtered transactions are shown.
Given a valid account number When a deposit is made Then the account balance increases.
Given an invalid account number When a deposit is attempted Then an error message is shown.
As a bank teller, I want to withdraw money from an account so that customers can receive their funds.
Given sufficient balance When a withdrawal is processed Then the balance decreases successfully.
Given insufficient balance When withdrawal is attempted Then the transaction is declined.